## Slide 1: Analysis of algorithms
Lecture 14 : PERT Charts
Based on section 6.2

## Slide 2: What is a PERT chart?
Performance, evaluation and review technique
Projects have lots of activities
Some can absorb delays, others cannot
Identify the relationships between tasks to discover the critical path

## Slide 3: Example : create a website
First, we must enumerate the subtasks involved and how much time they take
Task | Description | Duration
T1 | Pick Colours | 1
T2 | Decide on sections | 5
T3 | Produce section icons | 2
T4 | Write section content | 7
T5 | Buy domain name | 1
T6 | Decide on web host | 4
T7 | Buy hosting package | 1
T8 | Deploy site | 2
T9 | Run advertising campaign | 2

## Slide 4: Example : create a website
First, we must enumerate the subtasks involved and how much time they take
Task | Description | Duration
T1 | Pick Colours | 1
T2 | Decide on sections | 5
T3 | Produce section icons | 2
T4 | Write section content | 7
T5 | Buy domain name | 1
T6 | Decide on web host | 4
T7 | Buy hosting package | 1
T8 | Deploy site | 2
T9 | Distribute credentials | 2
Task | Depends On
T1 | 
T2 | 
T3 | T1,T2
T4 | T2
T5 | 
T6 | 
T7 | T6,T5
T8 | T3,T4,T7
T9 | T8

## Slide 5: Example : create a website
Next, we can draw the directed, acyclic graph representing this task set
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0

## Slide 6: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6

## Slide 7: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6
3
4
7

## Slide 8: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6
3
4
7
8

## Slide 9: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6
3
4
7
8
9

## Slide 10: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6
3
4
7
8
9
10

## Slide 11: Example : create a website
Task | Depends | Duration
T1 |  | 1
T2 |  | 5
T3 | T1,T2 | 2
T4 | T2 | 7
T5 |  | 1
T6 |  | 4
T7 | T6,T5 | 1
T8 | T3,T4,T7 | 2
T9 | T8 | 2
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
Every edge is given a weight equal to the preceding task’s duration

## Slide 12: Example : create a website
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
Next, we try to figure out three things – the earliest a task can start, the latest it can start without delaying the project, and the resulting slack time
Early start
Late start
Slack

## Slide 13: Example : create a website
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
The start task can start at the start of the project – time 0, as it doesn’t have to wait for anything
0 |  | 

## Slide 14: Example : create a website
Other tasks can only start once the preceding task has ended, so their start time is the previous task’s start time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 

## Slide 15: Example : create a website
When can task 3 start?
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 

## Slide 16: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 

## Slide 17: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 

## Slide 18: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 

## Slide 19: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 

## Slide 20: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 

## Slide 21: Example : create a website
Other tasks can only start once all preceding tasks have ended, so their start time is the maximum of all previous tasks’ starts time plus the duration of the previous task
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 
16 |  | 

## Slide 22: Example : create a website
The latest the end task can start to avoid delaying the project is the same as its start time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 
16 |  | 

## Slide 23: Example : create a website
The latest the end task can start to avoid delaying the project is the same as its start time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 
16 |  | 16

## Slide 24: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 
16 |  | 16

## Slide 25: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 
14 |  | 14
16 |  | 16

## Slide 26: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 
5 |  | 
4 |  | 
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 27: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 
4 |  | 
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 28: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 29: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 30: Example : create a website
For a task t, its latest start time is set to the latest start time of the succeeding task minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 31: Example : create a website
What is the latest start time of task 2?
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 32: Example : create a website
For a task t, its latest start time is set to the minimum of the latest start times of the succeeding tasks minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 33: Example : create a website
For a task t, its latest start time is set to the minimum of the latest start times of the succeeding tasks minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 0
0 |  | 
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 34: Example : create a website
For a task t, its latest start time is set to the minimum of the latest start times of the succeeding tasks minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 0
0 |  | 10
0 |  | 
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 35: Example : create a website
For a task t, its latest start time is set to the minimum of the latest start times of the succeeding tasks minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 
0 |  | 9
0 |  | 0
0 |  | 10
0 |  | 7
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 36: Example : create a website
For a task t, its latest start time is set to the minimum of the latest start times of the succeeding tasks minus the duration of t
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 0
0 |  | 9
0 |  | 0
0 |  | 10
0 |  | 7
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 37: Example : create a website
For a task t, its slack is the difference between the latest start time and the early start time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 |  | 0
0 |  | 9
0 |  | 0
0 |  | 10
0 |  | 7
5 |  | 10
5 |  | 5
4 |  | 11
12 |  | 12
14 |  | 14
16 |  | 16

## Slide 38: Example : create a website
For a task t, its slack is the difference between the latest start time and the early start time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 | 0 | 0
0 | 9 | 9
0 | 0 | 0
0 | 10 | 10
0 | 7 | 7
5 | 5 | 10
5 | 0 | 5
4 | 7 | 11
12 | 0 | 12
14 | 0 | 14
16 | 0 | 16

## Slide 39: Example : create a website
The critical path is the set of tasks that have a slack of 0. These cannot be allowed to have any delay if the project is to finish on time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 | 0 | 0
0 | 9 | 9
0 | 0 | 0
0 | 10 | 10
0 | 7 | 7
5 | 5 | 10
5 | 0 | 5
4 | 7 | 11
12 | 0 | 12
14 | 0 | 14
16 | 0 | 16

## Slide 40: Example : create a website
The critical path is the set of tasks that have a slack of 0. These cannot be allowed to have any delay if the project is to finish on time
0
1
2
5
6
3
4
7
8
9
10
0
0
0
0
1
5
5
1
4
2
7
1
2
2
0 | 0 | 0
0 | 9 | 9
0 | 0 | 0
0 | 10 | 10
0 | 7 | 7
5 | 5 | 10
5 | 0 | 5
4 | 7 | 11
12 | 0 | 12
14 | 0 | 14
16 | 0 | 16